## Action items
Proposed Activities | Responsibility | Measures | Timeframe | Notes | Done | Outcome
Widely advertising the event on:
There will be a sailing day for one kiwi plus their parent on Camper boat(TNZ) during the Volvo stopover | Pete Dawson & David Abercrombie | Number of mentions on traditional and internet news media within a week of the prize being awarded | Organisation by August 2011. Run in March 2012 | Will depend on weather conditions and on willingness of Volvo teams to take young sailors on board - Update required | Arranged | Media opportunity to follow young sailors aboard the ocean-racing boats. Minimum exposure Twitter, blog and Opti-worlds website. Max would include TV coverage
We can also have day with Jez Fanstone(YachtingNZ Olympic Coach) on Coach Boat sailing Olympic Classes (probably 49er) for 4 kids from Pre Worlds. | Pete Dawson & David Abercrombie | Count the number of cross-linked 'follows' per month from August to March 2012 between the Opti worlds and Volvo sites. | August to March 2012 | Waiting for report of counts - update required | Arranged | Counts will provide an indication of how compartmentalised yachting spectators may be in their interests
TV | GROW | Number of timeslots obtained in both news and advertising | 31 May 2011 to report as organised | See Media plan - Update required |  | Opportunities through many youth media to see, and hear from real competitors from different countries doing exciting things.
Radio | GROW |  | 2011-06-30 | Zoe has spoken to Martin Tasker. No official slots but keen and will cover something. Update required
Facebook | Selected competitors, Dave Merton, Brian Haybittle | followers | TBA | Update required. Competitions running
Website | Brian Haybittle | http://www.optiworldsnz.org.nz/
Provide the opportunity for foreign teams to enjoy the experience of YNZ certified Optimist coaching at the event | Adrian Mannering | Number of coaches engaged by foreign teams for pre-worlds clinic, and for the Worlds championships themselves | Bookings should be complete by 1 December, but reviewed 1 Feb | Update required - need current count | Expecting results by end of November | Opportunity to showcase NZ's world class optimist coaching. Opportunity for coaches to build relationships and experience with overseas teams
Work with active NZ Opti clubs and key commercial Opti coaches to develop an international off-season coaching opportunities for foreign teams. | David Abercrombie, Adrian Mannering, Andrew Brown, | Registrations of interest received during and after the World Optimist event | TBA but 30 April 2011 | Andrew is currently coaching two older Brazilian sailors for a month This is quite a complex opportunity. It requires the provision of schooling, pastoral care, home support and management as well as provision of boats and coaching for teams of typically 5-10 children under 15 for periods of 1-4 months. |  | New Industry, impacting both Opti coaching and education
Napier Produce & Souvenirs : Proposed "Friends of the Opti World's" programme with local retailers | Nigel &Megan Mannering | Increased volume estimates from participating vendors | Days have been decided. One morning and one twilgiht market to run. | Update Required. The concept is to advertise the "Friends" programme with discount vouchers and offers to be included in the welcome packs provided to the teams and supporters on arrival |  | A wider sampling and awareness of the Napier/Hawkes bay souvenir and produce market than might otherwise be available to the event participants. Likely increase to consumption
A Waka will be available throughout the NZ Opti worlds. Details to be advised by Marie Edwards | Phil Turner, Marie@Wakarides.co.nz | Number of people booking as part of the Optimist worlds groups | 2011-06-30 | Update required. Use Radio spots and get included on the council programme . Obtain footage of the waka and place on opti website. Moya to Contact Murray Sawyer and Simon Nixon ( Hastings District Council) |  | Unique NZ/Maori experience
Working through the Napier City Council the organising committee is hoping to provide a suitable Maori welcome and farewell for teams and dignitaries. The welcome is to be held at the Sound Shell on New Year's Eve. | Tania Broome | Number of attendees | 2011-06-30 | 75% complete at the beginning of August |  | Unique NZ/Maori experience
i-site is to be invited to set up within the Napier Sailing club grounds to provide an immediate source of information for visitors to the event | Keith Price and Annie Dundas | Number of people using the i-site onsite | 2012-01-30 | Update Required I-site have confirmed a portable unit on the ground at Napier Yacht club. Keith to review possibility of subsidised or free shuttle to Opti worlds attendees (Passes in the registration pack?) to aid their getting to town to spend their money. Possible contact Tourism NZ |  | Wider promotion of the attractions of the local area at more convenience to event guests than would otherwise be possible
A lay-day is planned for 6 January 2012 in the middle of the event. It is intended to offer several local tourist events. | Bridget Ormond | Number of people booking as part of the Optimist worlds groups | to organise: 1 May 2011 | recently appointed. to report next month |  | Opportunities for visitors to experience something that is Unique to NZ
Event VIPs include Team Managers, Political figures, Yachting personalities, Sponsors and Media personalities. The VIP list will be identified in more detail closer to the event itself. | World Opti Committee | See VIP list in end sheet of the spreadsheet | 2011-08-31 | Invitations sent? Update required Opening ceremony and celebrations (31/12/2011), yachting charter to view the racing on Day one, NZ IODA party 2/1/2012. VIP passes for other meals and opportunity to take up discounted accomodation |  | A welcoming experience for teams and VIP's alike
Legacy VIP's identified and Invited | Major Events | Legacy VIP list completed and VIPs invited | 2011-10-30 | Update required Note: Any event organisers attending the NZ Opti worlds will be very welcome, but will be expected to cover all their own costs. |  | Planning and appropriate support are in place to provide sufficient logistics and a great experience for our Legacy VIP's
i-site is to be invited to set up within the Napier Sailing club grounds to provide an immediate source of information for visitors to the event | Keith Price and Annie Dundas | Number of people using the i-site onsite | 2012-01-30 | Update Required I-site have confirmed a portable unit on the ground at Napier Yacht club. Keith to review possibility of subsidised or free shuttle to Opti worlds attendees (Passes in the registration pack?) to aid their getting to town to spend their money. Council response to street flag request? |  | Wider promotion of the attractions of the local area at more convenience to event guests than would otherwise be possible
Legacy VIP's identified and Invited | Major Events | Legacy VIP list completed and VIPs invited | 2011-10-30 | No Legacy VIP's identified as at October 2011 Note: Any event organisers attending the NZ Opti worlds will be very welcome, but will be expected to cover all their own costs. |  | Planning and appropriate support are in place to provide sufficient logistics and a great experience for our Legacy VIP's
It is proposed that the selected 'Capability' VIP's will be provided with a liaison and support person, and will be guided on a 1-day "behind the scenes" tour which will cover the planning and methodology used to develop the event together with an opportunity to see that put into place. | Peter Dawson, Lisa Gibson, Moya Bawden | Satisfaction survey from participating observer VIP's | Notification of VIP number for this capability group by August 31. | No Capability VIP's identified to date. Group to be hosted at no cost to the World Opti committee |  | Ability to pass on lessons learned directly
Registering on VolunteerNet | Maryanne Turner | Numbers of volunteers from all sources to be recorded | 2012-01-01 | First volunteer meeting held Wed 5/10/11, current number of volunteers approaching 100. Volunteer net is in use. Volunteer on Volunteer net.
The Volunteer Network will actively assist promoting all aspects of the Event - Athlete participation, event Volunteers, event Spectators | World Optimist Committee | Number of volunteers sourced through the site | 2011-11-30 | See main plan under volunteer training for discussion of quality management. |  | Increasing the pool of event volunteers able to provide assistance to other major events
Pan Pacific travel have been contracted to provide appropriate pre and post travel options. | Pan Pacific travel, World Opti committee | Count in person-days of additional travel booked by groups associated with the event that are beyond the event-days themselves. Note of aggregate average travel-spend outside Napier for this group | 2012-01-30 | Poor numbers . Bookings dirct thru internet |  | Estimate of additional spend in NZ directly from this event

## All Items
STIMULATE AND INCREASE PARTICIPATION IN OPTIMIST SAILING IN NZ
Objectives:
§ To stimulate and increase New Zealanders participation in Optimist sailing.
§ Programmes specifically targets children under 15 years and their parents.
Proposed Activities | Responsibility | Measures | Timeframe | Notes | Done | Outcome
Create and accept terms of Reference | Moya Bawden | Terms of referrence accepted | 2011-08-01 | Vote taken on terms of reference and accepted | 2011-08-03
Widely advertising the event on:
There will be a sailing day for one kiwi plus their parent on Camper boat(TNZ) during the Volvo stopover | Pete Dawson & David Abercrombie | Number of mentions on traditional and internet news media within a week of the prize being awarded | Organisation by August 2011. Run in March 2012 | Will depend on weather conditions and on willingness of Volvo teams to take young sailors on board | Arranged | Media opportunity to follow young sailors aboard the ocean-racing boats. Minimum exposure Twitter, blog and Opti-worlds website. Max would include TV coverage
We can also have day with Jez Fanstone(YachtingNZ Olympic Coach) on Coach Boat sailing Olympic Classes (probably 49er) for 4 kids from Pre Worlds. | Pete Dawson & David Abercrombie | Count the number of cross-linked 'follows' per month from August to March 2012 between the Opti worlds and Volvo sites. | August to March 2012 | Waiting for report of counts | Arranged | Counts will provide an indication of how compartmentalised yachting spectators may be in their interests
| Opti Worlds committee | Numbers of bumper stickers distributed | due 15 April 2011 | Consider negotiating with 470 organisers/YNZ to allow top 2-3 NZ contenders at the worlds to have 2-3 days hosted by YNZ in Auckland. Prize could incorporate time with YNZ, 470's regatta, meeting NZ's best sailors Tom Ashley & Jo Aleh and a visit to Team NZ (e.g. "Back stage passes" for the winners where they meet the team, designers, Grant Dalton etc). | Done | Wider brand awareness of the event NZ wide.
Providing the opportunity at the event, to have a go:
Yachting NZ (YNZ) is able to provide 6 optis and an additional larger craft for use on the pond at Napier to allow the public to ‘have a go’ during the Worlds. The provision of experienced tutors is included. | David Abercrombie | Count numbers of people who ‘have a go’ during the event | Due in place for the 11 days of the Worlds Dec 31 2011 to Jan 10 2012. | It is intended that NZIODA will have a full list of Opti sailing clubs and contact details on hand for interested members of the public. Arrange accomodation for 'Have a go" staff from Yachting NZ | Organised | Having a go right in the middle of the world’s highest achievers in the sport helps to cement the sense of excitement and achievement possible for very young sailors in this boat.
In addition YNZ is providing radio controlled boats which will allow those initially unwilling to get wet sailing an opportunity to build the thinking & strategies required for sailing. | David Abercrombie | Count the number of people who enter the radio controlled boat competition during the event | Due in place for the 11 days of the Worlds Dec 31 2011 to Jan 10 2012 | Signage ? Radio advertising? Possibility for Air NZ to sponsor the 'Have a go" | Organised
Provide the opportunity for the public to get out on the water to see the world’s top competitors sailing hard. Half day cruises are planned, with GPS and live streaming on board. | NZ Worlds Optimist committee | Count number of passengers on craft through the regatta. Try to verify if public or associated with competitors | Charter confirmed by 30/4/2011 |  | Done | Possibility of getting people on the water who haven't been there before. Use the opportunity to invite those present to " Have a go"
Double decker bus in Napier | Keith Price & Phil Turner | Small random phone poll Napier on event awareness 1 & 3 months out. Define source of information, if known. Committee to discuss funding and admin with Council | Signs in place by 1 October | Please note: there is significant cross-over here with the marketing plan. Signage has been sent | Done 1/8/11
TV | Pete Dawson for National TV, Annie Dundas for local TV | Number of timeslots obtained in both news and advertising | 31 May 2011 to report as organised | See Media plan |  | Opportunities through many youth media to see, and hear from real competitors from different countries doing exciting things.
Event CD/ Documentary | Phil Turner, David Abercrombie, Kevin Brown | Icarus productions from Greece | TBA | Investigations on most appropriate methods | Organised 1/8/11 | Opportunity to provide graphical evidence of event competence to other world yachting events
Radio | Phil Turner |  | 2011-06-30 | Zoe has spoken to Martin Tasker. No official slots but keen and will cover something
Website with GPS and video clips | Dave Merton & Event Camera | Hits | Dates for electronic media and other features TBA | Brian Haybittle to produce figures from the website | Done
You-Tube | Dave Merton & Event Camera, Brian Haybittle | Hits | TBA | Opti-clips already there. Brian Haybittle | 1st You-tube items up in July 2011
Twitter | Selected competitors, Dave Merton, Brian Haybittle | followers | TBA
Blog | Phil Turner, Brian Hay-Bittle, Social Kiwi | Hits | 2011-06-30 | Possibility for kids blog competition. Review options for prizes for this. Not limited to actual sailors.
Facebook | Brian Haybittle | Likes | 2011-08-01 | Facebook profiles up for: The event as a whole, each team and facebook competitions planned | 2011-08-01 | Measures will be in traffic and likes. Careful measurement around before and after competitions
Link to yachting NZ | Pete Dawson |  | 2011-07-30 |  | Done
National Newspapers | Ray Steele |  | 2011-08-01 | See Marketing plan | Planned and first release complete | Launch date of 1 August 2011
Local Newspapers | Grow |  | 2011-08-01 | See Marketing plan | Planned and first release complete | Launch date of 1 August 2012
BUSINESS RELATIONS PROGRAMME
Objectives:
§ Identifying business opportunities and the chance to showcase NZ expertise in several potentially export earning sectors of the economy.
§ Providing opportunities for those sectors to be present and promote their goods and services at the event
Proposed Activities | Responsibility | Measures | Timeframe | Notes |  | Outcome
Consider the possibility of linking the boat-builders website, both NZ Marine and the Rib manufacturers, to the NZ World Opti Website | Worlds Committee/Boat manufacturers | Number of follows per link | 2011-06-30 | Southern Pacific, the Rib manufacturers are on our website, and they will be linking Opti workds website. After Opti worlds, ask Southern Pacific for an assessment of what, if any, business they achieved from the link. | Ask grow for regular link-counts from the Opti-worlds website. | All coach boats built for the worlds have already been pre-sold to NZ Yacht clubs at a discount, and this will help to enhance the safety and ability of these clubs to serve young sailors over the next 10 years
Provide the opportunity for foreign teams to enjoy the experience of YNZ certified Optimist coaching at the event | Adrian Mannering | Number of coaches engaged by foreign teams for pre-worlds clinic, and for the Worlds championships themselves | Bookings should be complete by 1 December, but reviewed 1 Feb |  | Expecting results by end of November | Opportunity to showcase NZ's world class optimist coaching. Opportunity for coaches to build relationships and experience with overseas teams
Work with active NZ Opti clubs and key commercial Opti coaches to develop an international off-season coaching opportunities for foreign teams. | David Abercrombie, Adrian Mannering, Andrew Brown, | Registrations of interest received during and after the World Optimist event | TBA but 30 April 2011 | This is quite a complex opportunity. It requires the provision of schooling, pastoral care, home support and management as well as provision of boats and coaching for teams of typically 5-10 children under 15 for periods of 1-4 months. |  | New Industry, impacting both Opti coaching and education
Support Pacific Islands sailing through donations of sails, coaching and charter boat discount. NZ World Opti committee will be sponsoring the request to reduce entry fees to IODA from the Oceania nations | Peter Wilkinson | Volunteer coaches flew to the Cook Islands in July to help prep the national team there. |  |  | Done
NZ RIB manufacturers showcase. Manufacturer's literature to each National team | Peter Dawson | Registrations of interest in foreign purchase of new coach boats of the type to be built and used for the NZ Optimist worlds | Within 3 months of completion of World Optis | Literature is already on the website, and will go into the entry packs. Expecting 250 competitors and 150 officials, so at least 400 packs. | Done | Opportunity to showcase NZ's world class RIB manufacturing industry and provide the possibility for export sales
Napier Produce & Souvenirs : Proposed "Friends of the Opti World's" programme with local retailers | Annie Dundas, Keith Price, World Optimist Committee | Increased volume estimates from participating vendors | Days have been decided. One morning and one twilgiht market to run. | The concept is to advertise the "Friends" programme with discount vouchers and offers to be included in the welcome packs provided to the teams and supporters on arrival |  | A wider sampling and awareness of the Napier/Hawkes bay souvenir and produce market than might otherwise be available to the event participants. Likely increase to consumption
Yachting charters | Lyle Tresadern & Paul Redman | Number of charters directly related to the Opti worlds | Decision on how to advertise by 30/4. Charter report due 31 January 2012 | Charter yacht bookings to be set up on Optis website. Lyle to send link to Brian Haybittle | Due 1/9/2011 | Ability for overseas visiting adults to experience yachting themselves in premier NZ waters with expert support
PROMOTION OF NZ CULTURE & SPECIAL CHARACTER
Objectives:
* Celebrate the unique 'Art-Deco' architecture and feel of Napier City
* Provide opportunities to experience and explore aspects of Maori culture
* Provide opportunities to experience and explore unique flora and fauna of New Zealand
Proposed Activities | Responsibility | Measures | Timeframe | Notes |  | Outcome
Celebrating Napier's status as NZ Art Deco capital, providing vintage car transport and a short art-deco tour through the city on the way to the official welcome | Annie Dundas, World Optimist Committee | Number of dignitaries transported in vintage cars |  | Transport at risk if cruise ship visit clashes. Currently not an issue but watching brief being managed by Opti worlds committee | Done | Unique Napier/Art-Deco experience
A Waka will be available throughout the NZ Opti worlds. Details to be advised by Marie Edwards | Annie Dundas, Phil Turner, Marie@Wakarides.co.nz | Number of people booking as part of the Optimist worlds groups | 2011-06-30 | Use Radio spots and get included on the council programme . Obtain footage of the waka and place on opti website. Moya to Contact Murray Sawyer and Simon Nixon ( Hastings District Council) |  | Unique NZ/Maori experience
Working through the Napier City Council the organising committee is hoping to provide a suitable Maori welcome and farewell for teams and dignitaries. The welcome is to be held at the Sound Shell on New Year's Eve. | Annie Dundas, Phil Turner, Peter Mooney, Marie Edwards and Tania Broome | Number of attendees | 2011-06-30 | 75% complete at the beginning of August |  | Unique NZ/Maori experience
i-site is to be invited to set up within the Napier Sailing club grounds to provide an immediate source of information for visitors to the event | Keith Price and Annie Dundas | Number of people using the i-site onsite | 2012-01-30 | I-site have confirmed a portable unit on the ground at Napier Yacht club. Keith to review possibility of subsidised or free shuttle to Opti worlds attendees (Passes in the registration pack?) to aid their getting to town to spend their money. Possible contact Tourism NZ |  | Wider promotion of the attractions of the local area at more convenience to event guests than would otherwise be possible
It is intended that all official participants will receive a crafted bone gift which will remind them of their unique experience at the NZ World Opti Championships | Peter Dawson to contact Karen Thompson for recommendations on supply. Moya to arrange sample survey | Sample survey guests for impressions on the event and the gifts | 2012-01-30 | The samples are being demonstrated at present. Hook for the boys and a koru for the girls | Organised | NZ gift
A lay-day is planned for 6 January 2012 in the middle of the event. It is intended to offer several local tourist events. | Annie Dundas | Number of people booking as part of the Optimist worlds groups | to organise: 1 May 2011 |  |  | Opportunities for visitors to experience something that is Unique to NZ
VIP RELATIONS PROGRAMME
Objectives:
* VIPs are welcomed and hosted in a manner that recognises their status, importance and influence. Ensuring a welcoming experience for VIPs enhances New Zealand’s reputation as a welcoming host country.
* VIPs are linked with New Zealand business leaders, patrons of yachting or government officials where appropriate to build and strengthen relationships that may bring about enduring benefits for New Zealand and New Zealanders.
Proposed Activities | Responsibility | Measures | Timeframe | Notes |  | Outcome
Event VIPs include Team Managers, Political figures, Yachting personalities, Sponsors and Media personalities. The VIP list will be identified in more detail closer to the event itself. | World Opti Committee | VIP Invite list as it stands is to include: Dean Barker (Emirates TNZ/Patron) Grant Dalton (Emirates TNZ) Jan Dawson (Chair and President of Yachting NZ) Barbara Arnott (Mayor of Napier) Lawrence Yule (Mayor of Hastings) John Key (Prime Minister & Minister of Tourism) Gerry Brownlee (Minister of Economic Development) Murray McCully(Minister of Sport) Chris Tremaine( Member of Parliament - Napier) Local Iwi Representative | 2011-08-31 | Opening ceremony and celebrations (31/12/2011), yachting charter to view the racing on Day one, NZ IODA party 2/1/2012. VIP passes for other meals and opportunity to take up discounted accomodation |  | A welcoming experience for teams and VIP's alike
Legacy VIP's identified and Invited | Major Events | Legacy VIP list completed and VIPs invited | 2011-10-30 | Note: Any event organisers attending the NZ Opti worlds will be very welcome, but will be expected to cover all their own costs. |  | Planning and appropriate support are in place to provide sufficient logistics and a great experience for our Legacy VIP's
VIP Liaison | Kevin Brown & Phil Turner | Post event satisfaction survey | 2012-02-01 | Each group of VIP's is expected to have their own volunteer liaison person who will, if possible, speak their language and will be trained as to how to handle various VIP requirements. There will be a daily briefing to which VIP's will be invited, together with a VIP area set aside for comfort, refreshment and business meetings
Events Planning
Elsewhere in the project plan several events are planned both on behalf of IODA and to welcome and celebrate Christmas and New Year with the overseas teams. VIP's will be catered for in each of these events, Including service, reserved seating, translation and individual volunteer liaison as described | Nigel Mannering and Peter Dawson | Event attendance | See Events management portion of project plan |  | Done | Unique NZ Christmas/New Year events experienced
BUILDING CAPABILITY TO MANAGE SIMILAR EVENTS
* Legacy VIP's will be persons identified by SPARC and Major Events as wishing to learn from the NZ World Optimist Championship event management will be provided with the opportunity to visit, observe and ask questions during the event
Proposed Activities | Responsibility | Measures | Timeframe | Notes |  | Outcome
IODA Event hosting - Party and care of IODA officials | Worlds committee | NZIODA members satisfaction Survey | 2012-01-31 | Please see the event management section of the plan for the several functions to be hosted on behalf of IODA | Done | Foster international relationships with IODA (See also VIP section) and demonstrate the capability to host this and other yachting events in NZ. (NB) this is the class with the most competitors.
Sharing the process | World Opti Committee | Documented plan provided to Major Events for future reference | 2011-07-31 | Plan has been accepted by Major Events | Done | Ease of planning improved for future events
It is proposed that the selected 'Capability' VIP's will be provided with a liaison and support person, and will be guided on a 1-day "behind the scenes" tour which will cover the planning and methodology used to develop the event together with an opportunity to see that put into place. | Peter Dawson, Lisa Gibson, Moya Bawden | Satisfaction survey from participating observer VIP's | Notification of VIP number for this capability group by August 31. | Group to be hosted at no cost to the World Opti committee |  | Ability to pass on lessons learned directly
CREATING AN ITF VOLUNTEER SUPPORT NETWORK
Objective:
* Develop a strong Volunteer base that can be used to promote and contribute to the NZ World Optimist Championships 2011, and be a resource for future Major Events (legacy)
Proposed Activities | Responsibility | Measures | Timeframe | Notes |  | Outcome
Registering on VolunteerNet | Maryanne Turner | Numbers of volunteers from all sources to be recorded | 2012-01-01
The Volunteer Network will actively assist promoting all aspects of the Event - Athlete participation, event Volunteers, event Spectators | World Optimist Committee | Number of volunteers sourced through the site | 2011-11-30 | See main plan under volunteer training for discussion of quality management. |  | Increasing the pool of event volunteers able to provide assistance to other major events
Pursue volunteers from clubs, especially parents bringing children to the pre-worlds clinic | Wayne Holt YNZ | Post event satisfaction survey | 2012-01-30 | This will be made available for response online with a specific section on the knowledge, willingness to help and feeling of welcome generated by volunteers to the event
OTHER IDENTIFIED OPPORTUNITIES (BUT OUTSIDE THE SCOPE OF THIS PLAN)
Objective: | Responsibility |  | Timeframe | Notes |  | Outcome
* Promote & encourage longer stay tourism post-World Championships
Proposed Activities | Responsibility | Measures | Timeframe | Notes |  | Outcome
Pan Pacific travel have been contracted to provide appropriate pre and post travel options. | Pan Pacific travel, World Opti committee | Count in person-days of additional travel booked by groups associated with the event that are beyond the event-days themselves. Note of aggregate average travel-spend outside Napier for this group | 2012-01-30 | Peter to request count from Pan-Pac |  | Estimate of additional spend in NZ directly from this event

## by person
Proposed Activities | Responsibility | Measures | Timeframe | Notes | Done | Outcome
A Waka will be available throughout the NZ Opti worlds. Details to be advised by Marie Edwards | Adrian , Marie@Wakarides.co.nz | Number of people booking as part of the Optimist worlds groups | 2011-06-30 | Update required. Truck required Use Radio spots and get included on the council programme . Obtain footage of the waka and place on opti website. Moya to Contact Murray Sawyer and Simon Nixon ( Hastings District Council) |  | Unique NZ/Maori experience
Provide the opportunity for foreign teams to enjoy the experience of YNZ certified Optimist coaching at the event | Adrian Mannering | Number of coaches engaged by foreign teams for pre-worlds clinic, and for the Worlds championships themselves | Bookings should be complete by 1 December, but reviewed 1 Feb | Update required - need current count | Expecting results by end of November | Opportunity to showcase NZ's world class optimist coaching. Opportunity for coaches to build relationships and experience with overseas teams
A lay-day is planned for 6 January 2012 in the middle of the event. It is intended to offer several local tourist events. | Bridget Ormond | Number of people booking as part of the Optimist worlds groups | to organise: 1 May 2011 | recently appointed. to report next month |  | Opportunities for visitors to experience something that is Unique to NZ
Work with active NZ Opti clubs and key commercial Opti coaches to develop an international off-season coaching opportunities for foreign teams. | David Abercrombie, Adrian Mannering, Andrew Brown, | Registrations of interest received during and after the World Optimist event | TBA but 30 April 2011 | Andrew is currently coaching two older Brazilian sailors for a month This is quite a complex opportunity. It requires the provision of schooling, pastoral care, home support and management as well as provision of boats and coaching for teams of typically 5-10 children under 15 for periods of 1-4 months. |  | New Industry, impacting both Opti coaching and education
TV | GROW | Number of timeslots obtained in both news and advertising | 31 May 2011 to report as organised | See Media plan - Update required |  | Opportunities through many youth media to see, and hear from real competitors from different countries doing exciting things.
Radio | GROW |  | 2011-06-30 | Zoe has spoken to Martin Tasker. No official slots but keen and will cover something. Update required
i-site is to be invited to set up within the Napier Sailing club grounds to provide an immediate source of information for visitors to the event | Keith Price and Annie Dundas | Number of people using the i-site onsite | 2012-01-30 | Update Required I-site have confirmed a portable unit on the ground at Napier Yacht club. Keith to review possibility of subsidised or free shuttle to Opti worlds attendees (Passes in the registration pack?) to aid their getting to town to spend their money. Council response to street flag request? |  | Wider promotion of the attractions of the local area at more convenience to event guests than would otherwise be possible
VIP Liaison | Kevin Brown & Phil Turner | Post event satisfaction survey | 2012-02-01 | VIP Liaison people identified ? Each group of VIP's is expected to have their own volunteer liaison person who will, if possible, speak their language and will be trained as to how to handle various VIP requirements. There will be a daily briefing to which VIP's will be invited, together with a VIP area set aside for comfort, refreshment and business meetings | Survey draft completed for review
Legacy VIP's identified and Invited | Major Events | Legacy VIP list completed and VIPs invited | 2011-10-30 | No Legacy VIP's identified as at October 2011 Note: Any event organisers attending the NZ Opti worlds will be very welcome, but will be expected to cover all their own costs. |  | Planning and appropriate support are in place to provide sufficient logistics and a great experience for our Legacy VIP's
Registering on VolunteerNet | Maryanne Turner | Numbers of volunteers from all sources to be recorded | 2012-01-01 | First volunteer meeting held Wed 5/10/11, current number of volunteers approaching 100. Volunteer net is in use. Volunteer on Volunteer net.
Napier Produce & Souvenirs : Proposed "Friends of the Opti World's" programme with local retailers | Nigel &Megan Mannering | Increased volume estimates from participating vendors | Days have been decided. One morning and one twilgiht market to run. | Update Required. The concept is to advertise the "Friends" programme with discount vouchers and offers to be included in the welcome packs provided to the teams and supporters on arrival |  | A wider sampling and awareness of the Napier/Hawkes bay souvenir and produce market than might otherwise be available to the event participants. Likely increase to consumption
Pan Pacific travel have been contracted to provide appropriate pre and post travel options. | Pan Pacific travel, World Opti committee | Count in person-days of additional travel booked by groups associated with the event that are beyond the event-days themselves. Note of aggregate average travel-spend outside Napier for this group | 2012-01-30 | Poor numbers . Bookings dirct thru internet |  | Estimate of additional spend in NZ directly from this event
There will be a sailing day for one kiwi plus their parent on Camper boat(TNZ) during the Volvo stopover | Pete Dawson & David Abercrombie | Number of mentions on traditional and internet news media within a week of the prize being awarded | Organisation by August 2011. Run in March 2012 | Will depend on weather conditions and on willingness of Volvo teams to take young sailors on board - Update required | Arranged | Media opportunity to follow young sailors aboard the ocean-racing boats. Minimum exposure Twitter, blog and Opti-worlds website. Max would include TV coverage
We can also have day with Jez Fanstone(YachtingNZ Olympic Coach) on Coach Boat sailing Olympic Classes (probably 49er) for 4 kids from Pre Worlds. | Pete Dawson & David Abercrombie | Count the number of cross-linked 'follows' per month from August to March 2012 between the Opti worlds and Volvo sites. | August to March 2012 | Waiting for report of counts - update required | Arranged | Counts will provide an indication of how compartmentalised yachting spectators may be in their interests
It is proposed that the selected 'Capability' VIP's will be provided with a liaison and support person, and will be guided on a 1-day "behind the scenes" tour which will cover the planning and methodology used to develop the event together with an opportunity to see that put into place. | Peter Dawson, Lisa Gibson, Moya Bawden | Satisfaction survey from participating observer VIP's | Notification of VIP number for this capability group by August 31. | No Capability VIP's identified to date. Group to be hosted at no cost to the World Opti committee |  | Ability to pass on lessons learned directly
Facebook | Phil Turner, Brian Hay-Bittle, Social Kiwi | Hits | 2011-06-30 | Possibility for kids blog competition. Review options for prizes for this. Not limited to actual sailors.Update required
Working through the Napier City Council the organising committee is hoping to provide a suitable Maori welcome and farewell for teams and dignitaries. The welcome is to be held at the Sound Shell on New Year's Eve. | Tania Broome | Number of attendees | 2011-06-30 | 75% complete at the beginning of August |  | Unique NZ/Maori experience
Event VIPs include Team Managers, Political figures, Yachting personalities, Sponsors and Media personalities. The VIP list will be identified in more detail closer to the event itself. | World Opti Committee | See VIP list in end sheet of the spreadsheet | 2011-08-31 | Invitations sent? Update required Opening ceremony and celebrations (31/12/2011), yachting charter to view the racing on Day one, NZ IODA party 2/1/2012. VIP passes for other meals and opportunity to take up discounted accomodation |  | A welcoming experience for teams and VIP's alike
The Volunteer Network will actively assist promoting all aspects of the Event - Athlete participation, event Volunteers, event Spectators | World Optimist Committee | Number of volunteers sourced through the site | 2011-11-30 | See main plan under volunteer training for discussion of quality management. |  | Increasing the pool of event volunteers able to provide assistance to other major events